## Sheet1
# | Stage | Job | SSIS Folder | SSIS Package Name
New Jobs that will be created for AUS Lease Data Integration
1 | SourceToStage | Yardi_Space | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_Space
2 | SourceToStage | Yardi_SpaceBuilding | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_SpaceBuilding
3 | SourceToStage | Yardi_AU_Tenant | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_AU_Tenant
4 | SourceToStage | Yardi_User | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_User
5 | SourceToStage | Yardi_RentChargeType | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_RentChargeType
6 | SourceToStage | Yardi_LeaseTermination | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_LeaseTermination
7 | SourceToStage | Yardi_LeaseSpace | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_LeaseSpace
8 | SourceToStage | Yardi_ LeaseRentalSchedule | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_ LeaseRentalSchedule
9 | SourceToStage | Yardi_LeaseRebate | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_LeaseRebate
10 | SourceToStage | Yardi_LeaseSpaceSummary | S_YardiToStage | DF_Lease_LoadSrcToStg_Yardi_LeaseSpaceSummary
Existing Jobs that are going to be modified for this AUS Lease Data Integration
11 | SourceToRef | R_DWAssetBuilding | D_DWAsset | DF_Lease_LoadStgToEDW_R_DWAssetBuilding
12 | SourceToRef | R_DWUser | R_DWUser | DF_Lease_LoadStgToEDW_R_DWUser
13 | SourceToRef | R_DWRentChargeType | R_DWRentChargeType | DF_Lease_LoadStgToEDW_R_DWRentChargeType
14 | SourceToDimension | D_DWAsset | D_DWAsset | DF_Lease_LoadStgToEDW_D_DWAsset
15 | SourceToDimension | D_DWTenant | D_DWTenant | DF_Lease_LoadStgToEDW_D_DWTenant
16 | SourceToDimension | D_DWAgreementType | D_DWAgreementType | DF_Lease_LoadStgToEDW_D_DWAgreementType
17 | SourceToDimension | D_DWLeaseActivity | D_DWLeaseActivity | DF_Lease_LoadStgToEDW_D_DWLeaseActivity
18 | StageToBaseLine | F_DWLeaseTermination | F_DWLeaseTermination | DF_Lease_LoadStgToEDW_F_DWLeaseTermination
19 | StageToBaseLine | F_DWLeaseSpaceSummary | F_DWLeaseSpaceSummary | DF_Lease_LoadStgToEDW_F_DWLeaseSpaceSummary
20 | StageToBaseLine | F_DWLeaseSpace | F_DWLeaseSpace | DF_Lease_LoadStgToEDW_F_DWLeaseSpace
21 | StageToBaseLine | F_DWLeaseRentSchedule | F_DWLeaseRentSchedule | DF_Lease_LoadStgToEDW_F_DWLeaseRentSchedule
22 | StageToBaseLine | F_DWLeaseRebate | F_DWLeaseRebate | DF_Lease_LoadStgToEDW_F_DWLeaseRebate
23 | StageToBaseLine | F_DWLeasePT | F_DWLeasePT | DF_Lease_LoadStgToEDW_F_DWLeasePT

## Sheet2
Data Objects | Development | Unit Testing
Asset | Completed | Completed
Tenant | Completed | Completed
User | Completed | Completed
RentChargeType | Completed | Completed
LeaseTermination | Completed | Completed
LeaseSpace | Completed | Completed
LeaseRentalSchedule | Completed | Progress
LeaseRebate | Completed | Progress
LeaseSpaceSummary | Completed | Progress
SnapShot Staging Data | Completed | To be Started
Fact Lease | N.A. | To be Started
Fact Asset | N.A. | To be Started
Master Control Flow | Progress | To be Started

## Sheet3
S/No | Activity | Status | Activity Target Date | Comments
1 | End Development | On Going | 29th Sep 2017 | Data validation between Yardi Source and APAS on Record Count and Key columns value match
2 | Prepare and complete UAT Test Cases | On Going | 22nd Sep 2017 | Setup meeting with Chin Sing and Yong Hui to discuss and prepare UAT test cases and detailed plan.
3 | Setup UAT environment | On Going | 22nd Sep 2017
4 | Complete SIT | Not Started | 06th Oct 2017 | Includes Pre-UAT validation. IT verify data between APAS and Manual Reports before releasing the report to UAT.
5 | Start and Complete UAT | Not Started | 20th Oct 2017 | UAT will be conducted from 9th Oct to 20th Oct. User should allocate their time during these period.

## Sheet4
S/No | Data Objects | Development | Unit Testing
1 | Asset | Completed | Completed
2 | Tenant | Completed | Completed
3 | User | Completed | Completed
4 | RentChargeType | Completed | Completed
5 | LeaseTermination | Completed | Completed
6 | LeaseSpace | Completed | Completed
7 | LeaseRentalSchedule | Completed | Progress
8 | LeaseRebate | Completed | Progress
9 | LeaseSpaceSummary | Completed | Progress
10 | SnapShot Staging Data | Completed | Not Started
11 | Fact Lease | N.A. | Not Started
12 | Fact Asset | N.A. | Not Started
13 | Master Control Flow | Progress | Not Started

## Sheet5
Data | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
abc1 | 4.8269 | 59.4269 | 944.839 | 850.0536 | 828.2183 | 479.4303 | 746.4057 | 116.8134
abc2 | 713.9261 | 935.1986 | 971.552 | 79.7661 | 934.3884 | 597.5375 | 509.6308 | 265.3672
abc3 | 292.0142 | 686.9245 | 275.6065 | 846.5358 | 41.0956 | 65.9343 | 304.2726 | 232.3433
abc4 | 712.3845 | 658.0175 | 949.8837 | 78.0969 | 92.3891 | 469.3379 | 584.4208 | 31.6751
abc5 | 270.0958 | 716.513 | 715.2328 | 760.4653 | 336.9327 | 215.6872 | 150.6826 | 751.743
abc6 | 19.9192 | 955.6712 | 82.6147 | 89.1654 | 254.6237 | 314.6327 | 262.7358 | 248.8971
abc7 | 894.4626 | 716.179 | 637.1029 | 190.9221 | 634.8741 | 14.737 | 619.0007 | 829.4485
abc8 | 739.3284 | 608.3436 | 829.4258 | 68.4108 | 690.4582 | 946.6098 | 872.9013 | 441.3737
abc9 | 256.9514 | 976.6237 | 347.6156 | 150.1224 | 515.5402 | 659.9319 | 770.3865 | 544.5802